## Sheet1
file_name | group | file_type | dates | wells | summary | processed_at
UZ034 Procedure cut casing and surface plug rev 0.pdf | Other Group | pdf | ['18/05/2022', '2-1/16'] | ['WELL BARRIERS', 'WELL SCHEMATIC', 'wellhead', 'Well \n \n21', 'well is', 'Well \nUZ034', 'well and', 'Wellhead', 'Well Interventions', 'Well \n \n10', 'well bore', 'Well Survey', 'Well specific', 'well with', 'well for', 'Well \n \n18', 'well site', 'Well Schematic', 'well displace', 'Well \n \n12', 'well in', 'Well \n \n6', 'Well barriers', 'Well \n \n15', 'Well \n \n22', 'Well \n \n9', 'Well \n \n1', 'WELLHEAD', 'Well Barriers', 'Well \n \n5', 'Well \n \n3', 'Well \n \n20', 'Well \n \n7', 'well suspension', 'Well \n \n4', 'Well \n \n17', 'Well \n \n13', 'well back', 'Well Integrity', 'Well \n \n2', 'Well \n \n16', 'Well Testing', 'WELL SUSPENSION', 'Well \n \n8', 'Wellbore', 'Well \n \n19', 'Well \n \n14', 'Well Barrier', 'Well \n \n11'] | The document outlines the procedure for plugging and abandoning well UZ034 on platform PC013, including cutting and pulling casings, and placing surface cement plugs, with operations beginning at 1500' and involving multiple steps such as cutting the 10-3/4” casing at +180’ below seabed level and the 13-3/8” casing at +160 ft. below seabed level. The procedure was prepared by Faisal S. AL Zaabi and reviewed by various engineers, with final approval by Melanie Mikula and George Jarvis. | 2025-07-15T05:10:15.505528
Hazard Analysis and Risk Control (Risk Assessment).pdf | Risk Assessment and Hazard Analysis | pdf | ['08/30/2020', '10/07/2022', '60/40-70'] | ['Well \nControl', 'well Well', 'Well kill', 'Well-bore', 'Well Killing', 'Well control', 'wellbore', 'Well \ncontrol', 'well \nLoss', 'Wellbore', 'Well Control'] | The Hazard Analysis and Risk Control Report (RA-2020-000007) for PPC Drilling Fluids/Offshore, assessed on 08/30/2020, identifies key risks and control measures for drilling operations involving BENTONITE polymer mud, including well control events, stuck pipe, and loss of tools/BHA, with specific mitigation strategies such as maintaining sufficient barite stocks and preparing for cement plugs. The assessment, created by Fath Elfahal and last modified on 10/07/2022, involves 12 exposed personnel and includes detailed risk matrices and preventative measures for various drilling scenarios. | 2025-07-15T05:10:17.043193
PPC Mud Program UZ- 034 Rig Diyina_Cut Casing and Surface Plug_Rev 2.pdf | Mud Program | pdf | ['4/10/2014', '6/23/2016'] | ['WELL SCHEMATIC', 'wellhead', 'Well Cost', 'well is', 'well and', 'well bore', 'Well Kill', 'well with', 'Well Control', 'Well Schematics', 'well for', 'well site', 'Well Schematic', 'well displace', 'well in', 'WELL CURRENT', 'Well Chemicals', 'Well UZ-034', 'WELL SCHEMATICS', 'Well Suspension', 'wells', 'Well History', 'wellbores', 'well within', 'wellbore', 'WELL KILL', 'well\n0', 'WELL HISTORY', 'well control', 'WELL SYNOPSIS', 'WELL CHEMICALS', 'well back', 'well deviation', 'well the', 'Well Current'] | The document "PPC Mud Program UZ-034 Rig Diyina_Cut Casing and Surface Plug_Rev 2" outlines the drilling fluids program for well UZ-034 (PC 13) on Rig Diyina, detailing operations such as cutting casing and installing a surface plug, with key dates including preparation on 26-May-2022 and approval on 27-May-2022. The document includes a comprehensive overview of well history, current status, operational procedures, and safety considerations, spanning 56 pages. | 2025-07-15T05:10:18.935839
Diyina - UZ-034- Engineering Ticket 1.pdf | Engineering Tickets | pdf | ['01/06/2022', '24/06/2022'] | ['well site', 'WELL NO', 'well during'] | The document "Diyina - UZ-034- Engineering Ticket 1" details the engineering services provided by Petrochem Performance Chemicals Limited L.L.C. for ADNOC Offshore on Rig Diyina, Well No. UZ-034, from June 1 to June 24, 2022, with Thirumoorthi as the Petrochem representative and Muhammad Umar Saleem as the company representative. The service quality assessment rated the performance as exceeding expectations in all categories, with specific commendation for Thirumurugan's dedication and performance. | 2025-07-15T05:10:30.728517
Diyina - UZ-034 - Chemical Consumption.pdf | Chemical Consumption | pdf | [] | [] | The document "Diyina - UZ-034 - Chemical Consumption" details the chemical usage for well LZ-394 operated by ADNOC Offshore (LZ) on the rig DYNA-MAC, with operations starting on 03.05.22 and the report submitted on 24.05.22 by Mud Engineer Thirumurugan Arumugam. Key chemicals used include TRISALAN S and NOCO-LOX HS, with consumption tracked over a 22-day period. | 2025-07-15T05:10:36.269770
Service Data Contractor Feedback - UZ-034 Diyina.pdf | Contractor Feedback | pdf | ['24/06/2022'] | ['well reports', 'well report', 'Well Name'] | On June 24, 2022, Petrochem provided drilling fluids services for well UZ-034 on the Diyina rig, with no deficiencies observed in mud chemicals, engineering support, lab equipment, or report submissions, achieving a Fluids Business Support Index Score of 100. The actual total volume of 11.6 ppg CaCl2/CaBr2 brine handled was 1023 bbl, slightly below the planned 1099 bbl, resulting in a volume ratio of 0.93%. | 2025-07-15T05:10:37.432624
DF Contractor Feedback Form_Database_up to UZ-34.pdf | Contractor Feedback | pdf | ['25/6/2022'] | ['Well Date', 'Well Feedback', 'Well Name'] | The Drilling Fluids Well Feedback Form for well UZ-034, drilled by rig DIYINA, details operations from June 3, 2022, to June 24, 2022, including the preparation of 1,023 bbl of 11.6 ppg CaCl2/CaBr2 kill fluid and a cost variance of 22.97% per barrel. | 2025-07-15T05:10:38.350905
Diyina - UZ-034- Well Recap.pdf | Well Recap | pdf | ['03/06/2022', '24/06/2022'] | ['Well ID', 'well for', 'well to', 'well back', 'well static', 'Well Summary', 'well test', 'well stable', 'Well Name', 'well UZ-506', 'well with', 'Well \nUZ', 'well \nRig'] | The final recap for well UZ-034, operated by ADNOC Offshore UZ and drilled by ADNOC Drilling, details operations from June 3 to June 24, 2022, including the use of CaCl2/CaBr2 brine for a 1,500 ft interval with a total mud cost of $58,157.16. Key operations included cement plug installations, casing cutting, wireline TCP gun operations, and conductor cutting, with significant activities such as the retrieval of 10-3/4" casing and the handling of 1,023 bbl of 11.6 ppg brine. | 2025-07-15T05:10:40.329851
UZ046 Procedure 1 - Well Access and Cleanout_SS - Copy.pdf | Well Recap | pdf | ['15/04/2022', '2-1/16', '4-21/64'] | ['WELL SCHEMATIC', 'wellhead', 'Well \n \n21', 'well head', 'well is', 'Well \n \n35', 'well and', 'Wellhead', 'Well \n \n27', 'Well no', 'Well Interventions', 'Well \n \n10', 'well \ntest', 'well as', 'Well \n \n28', 'Well Survey', 'well access', 'Well specific', 'well testing', 'Well Kill', 'Well Access', 'Well Control', 'Well \n \n25', 'Well \n \n18', 'Well \nUZ046', 'Well \n \n24', 'Well Schematic', 'Well \n \n29', 'Well \n \n37', 'Well \n \n38', 'Well \n \n12', 'Well \n \n6', 'Well \n \n19', 'Well \n \n30', 'WELL CURRENT', 'well integrity', 'Well \n \n26', 'well \nintegrity', 'WELL TESTING', 'Well \n \n15', 'Well testing', 'Well \n \n9', 'Well \n \n22', 'Well \n \n1', 'Well \n \n34', 'WELLHEAD', 'Well Barriers', 'Well \n \n31', 'Well \n \n5', 'Well \n \n3', 'Well History', 'well test', 'Well Volumes', 'Well \n \n20', 'Well \n \n7', 'WELL HISTORY', 'well are', 'well control', 'Well \n \n33', 'Well \n \n4', 'Well \n \n17', 'Well \n \n36', 'Well \n \n13', 'Well \n \n16', 'Well Integrity', 'Well \n \n2', 'Well Testing', 'Well \n \n23', 'well was', 'Well \n \n8', 'Well \n \n32', 'Wellbore', 'Well Current', 'Well \n \n14', 'Well Barrier', 'Well \n \n11'] | The document outlines the procedure for accessing and cleaning out well UZ046, a P&A injector well located on platform PW133, drilled by rig Diyina. Key dates include the initial drilling in April 1978 to a total depth of 10,503 feet, further drilling and completion in February 1984, preservation in July 1999, and a visual inspection in January 2013. | 2025-07-15T05:10:41.594037
UZ046 Procedure 2 - Cement plug 1 and 2.pdf | Other Group | pdf | ['17/04/2022', '2-1/16', '4-21/64'] | ['WELL BARRIERS', 'WELL SCHEMATIC', 'wellhead', 'Well \n \n21', 'well head', 'well is', 'Well \n \n39', 'Well \n \n35', 'Wellhead', 'Well \n \n27', 'Well Interventions', 'Well \n \n10', 'Well \n \n28', 'Well Survey', 'well access', 'Well specific', 'Well Control', 'well for', 'Well \n \n25', 'Well \n \n18', 'Well \nUZ046', 'Well \n \n24', 'Well Schematic', 'Well \n \n29', 'Well \n \n37', 'Well \n \n38', 'Well \n \n12', 'Well \n \n6', 'Well \n \n30', 'well integrity', 'Well \n \n26', 'Well \n \n15', 'Well \n \n22', 'Well \n \n9', 'Well \n \n34', 'Well \n \n1', 'WELLHEAD', 'Well Barriers', 'Well \n \n31', 'Well \n \n5', 'Well \n \n3', 'wellbore', 'Well Volumes', 'Well \n \n20', 'Well \n \n7', 'well control', 'Well \n \n33', 'Well \n \n4', 'Well \n \n17', 'Well \n \n36', 'Well \n \n13', 'Well \n \n16', 'Well Integrity', 'Well \n \n2', 'Well Testing', 'Well \n \n23', 'Well \n \n8', 'Well \n \n32', 'Wellbore', 'Well \n \n19', 'Well \n \n14', 'Well Barrier', 'Well \n \n11'] | The document "UZ046 Procedure 2 - Cement plug 1 and 2.pdf" outlines the procedure for cementing the upper and lower zones of well UZ046 on platform PW133, using rig Diyina. Key operations include setting a Mechanical Cement Retainer, pressure testing to 1,000 psi, and pumping cement plugs, with specific reservoir pressures noted at 3,850 psi and 3,900 psi for Thamama IA and IIA respectively. | 2025-07-15T05:10:42.986912
UZ046 Procedure 3 - Cement plug 3 rev1.pdf | Other Group | pdf | ['2-1/16', '26/04/2022', '4-21/64'] | ['WELL BARRIERS', 'WELL SCHEMATIC', 'Well \n \n21', 'well is', 'Well barrier', 'Wellhead', 'Well \n \n27', 'Well Interventions', 'Well \n \n10', 'Well \n \n28', 'Well Survey', 'well access', 'Well specific', 'Well Control', 'Well \n \n25', 'Well \n \n18', 'Well \nUZ046', 'well UZ-046', 'Well Schematic', 'Well \n \n24', 'Well \n \n29', 'Well \n \n12', 'Well \n \n6', 'Well \n \n30', 'Well \n \n26', 'Well \n \n15', 'Well \n \n22', 'Well \n \n9', 'Well \n \n1', 'WELLHEAD', 'Well Suspension', 'Well Barriers', 'Well \n \n31', 'Well \n \n5', 'Well \n \n3', 'wellbore', 'Well \n \n20', 'Well \n \n7', 'well control', 'Well \n \n4', 'Well \n \n17', 'Well \nKilling', 'Well \n \n13', 'Well \n \n16', 'Well Integrity', 'Well \n \n2', 'Well killed', 'Well Testing', 'Well \n \n23', 'Well \n \n8', 'Well \n \n32', 'Wellbore', 'Well \n \n19', 'Well \n \n14', 'Well Barrier', 'Well \n \n11'] | The document "UZ046 Procedure 3 - Cement plug 3 rev1.pdf" outlines the procedure for setting Cement Plug #3 in Well UZ046 on Platform PW133, operated by ADNOC Offshore, with key operations including perforating the Fiqa formation at 6,000-6,150 feet and subsequent cementing steps, prepared by Completion Engineer Osama Al Khatib and approved by Engineering Manager Melanie Mikula. | 2025-07-15T05:10:44.127624
UZ046 Procedure 4 - Cut casing and surface plug_v1.docx | Other Group | docx | ['2-1/16', '27/04/2022', '4-21/64'] | ['wellhead', 'well is', 'well and', 'Wellhead', 'Well Interventions', 'Well Survey', 'Well specific', 'well with', 'well for', 'well site', 'Well Schematic', 'well displace', 'well in', 'Well barriers', 'Well Barriers', 'well suspension', 'well back', 'Well Integrity', 'Well Testing', 'Wellbore', 'Well Barrier'] | The document "UZ046 Procedure 4 - Cut casing and surface plug_v1" outlines the steps for installing permanent abandonment barriers, including cutting and pulling 10-3/4” casing at 180’ below seabed level and 13-3/8” casing at 160’ below seabed level, followed by placing a balanced cement plug from 500 ft. to 80 ft. above seabed level. The procedure includes detailed operational steps, safety measures, and compliance with ADNOC OFFSHORE rules, with key operations such as N/D BOP, N/U BOP, and monitoring well stability. | 2025-07-15T05:10:46.219555
Hazard Analysis and Risk Control (Risk Assessment).pdf | Risk Assessment and Hazard Analysis | pdf | ['08/30/2020', '10/07/2022', '60/40-70'] | ['Well \nControl', 'well Well', 'Well kill', 'Well-bore', 'Well Killing', 'Well control', 'wellbore', 'Well \ncontrol', 'well \nLoss', 'Wellbore', 'Well Control'] | The Hazard Analysis and Risk Control Report (RA-2020-000007) for PPC Drilling Fluids/Offshore, assessed on 08/30/2020, details various risks and control measures for drilling operations, including the use of BENTONITE polymer mud in 16" holes and 12 1/4" NAF wells, with key risks such as stuck pipe, well control events, and loss of tools/BHA, and specifies preventive measures like maintaining sufficient barite stocks and preparing for cement plugs. The assessment team included Mohamed Farouk and Patrik Cekada, with the last modification made by Fath Elfahal on 10/07/2022. | 2025-07-15T05:10:47.795717
PPC Mud Program UZ 046_Cement Plug 3 and 4– Procedure 3 of 4.pdf | Mud Program | pdf | ['28-10-2020', '4/10/2014', '6/23/2016'] | ['WELL SCHEMATIC', 'Well Cost', 'Well UZ', 'well is', 'Well Kill', 'Well Control', 'Well Schematic', 'Well UZ-046', 'Well Chemicals', 'wells', 'wellbores', 'well within', 'wellbore', 'WELL KILL', 'well control', 'WELL SYNOPSIS', 'WELL CHEMICALS', 'well \n0', 'well deviation', 'well the'] | The document outlines the drilling fluids program for Well UZ-046 (PW 133) on Rig Diyina, focusing on the procedures for Cement Plugs #3 and #4, prepared by PPC Project Engineer Andrey Ulyashev on April 28, 2022, and approved by Ahmed Rashed Alaleeli on April 29, 2022. | 2025-07-15T05:10:48.884475
PPC Mud Program UZ 046_Cement Plug 5 Procedure 4 of 4_signed.pdf | Mud Program | pdf | ['28-10-2020', '4/10/2014', '6/23/2016'] | ['WELL SCHEMATIC', 'WELL COST', 'wellhead', 'Well UZ-', 'well is', 'Well Cost', 'well and', 'Well Kill', 'well with', 'Well Control', 'well for', 'well site', 'Well Schematic', 'Well UZ-046', 'well displace', 'well in', 'Well Chemicals', 'wells', 'wellbores', 'well within', 'well cost', 'wellbore', 'Well Synopsis', 'WELL KILL', 'well control', 'well suspension', 'WELL SYNOPSIS', 'WELL CHEMICALS', 'WELL \nCOST', 'well \n0', 'well back', 'well deviation', 'WELL SUSPENSION', 'well the'] | The document "PPC Mud Program UZ 046_Cement Plug 5 Procedure 4 of 4_signed.pdf" outlines the drilling fluids program for Well UZ-046 (PW 133) on Rig Diyina, focusing on the cut casing and surface plug operations conducted in May 2022. Key personnel involved include PPC Project Engineer Andrey Ulyashev, who prepared the document on April 29, 2022, and it was approved by Ahmed Rashed Alaleeli on May 1, 2022. | 2025-07-15T05:10:50.860473
Mud Program UZ 046 Rig Diyina_Procedure 2 of 4_signed.pdf | Mud Program | pdf | ['4/10/2014', '6/23/2016'] | ['WELL SCHEMATIC', 'wellhead', 'Well UZ-', 'well head', 'well is', 'Well Cost', 'Well Kill', 'Well Control', 'well for', 'Well Schematic', 'Well UZ-046', 'Well Chemicals', 'wells', 'wellbores', 'well within', 'wellbore', 'Well Volumes', 'WELL KILL', 'well control', 'WELL SYNOPSIS', 'WELL CHEMICALS', 'well \n0', 'well deviation', 'well the'] | The document outlines the drilling fluids program for Well UZ-046 (PW 133) on Rig Diyina, focusing on the procedures for Cement Plugs #1 and #2, prepared by PPC Project Engineer Andrey Ulyashev on April 22, 2022, and approved by Ahmed Rashed Alaleeli on April 23, 2022. The program includes detailed operational steps, well schematics, and safety considerations, spanning 59 pages. | 2025-07-15T05:10:52.215188
Diyina - UZ-046- Engineering Ticket 2.pdf | Engineering Tickets | pdf | ['01/05/2022', '08/05/2022'] | ['well site', 'WELL NO'] | The document "Diyina - UZ-046- Engineering Ticket 2.pdf" details the engineering service provided by Petrochem Performance Chemicals Limited L.L.C. for ADNOC Offshore on Rig DIYINA, Well No. UZ-046, from 01/05/2022 to 08/05/2022, with Thirumuruvan as the lead engineer. The service quality assessment, completed on 08/05/2022, indicates that the performance consistently exceeded expectations in all evaluated categories. | 2025-07-15T05:11:07.616925
Diyina - UZ-046- Engineering Ticket 1.pdf | Engineering Tickets | pdf | ['01/05/2022', '21/04/2022', '30/04/2022'] | ['well site', 'WELL NO'] | The document "Diyina - UZ-046- Engineering Ticket 1.pdf" details the engineering service provided by Petrochem Performance Chemicals Limited L.L.C. for ADNOC Offshore on Rig DIYINA, Well No. UZ-046, from 21/04/2022 to 30/04/2022, totaling 10 days, with the service quality assessment completed on 01/05/2022. The lead engineer, Thirumuruvan, received high marks across all categories, indicating exceptional performance and dedication. | 2025-07-15T05:11:28.241678
Diyina - UZ-046 - Chemical Consumption.pdf | Chemical Consumption | pdf | [] | [] | The document "Diyina - UZ-046 - Chemical Consumption" details the chemical usage for well UZ-046, operated by ADNOC Offshore, with operations starting on April 22, 2022, and the report submitted on May 8, 2022, highlighting the consumption of various chemicals such as TRUSOLV-HF and NOCOR 8 over the specified dates. The mud system used was a 10.2 Ppg CaCl2 Brine, and the report was prepared by Mud Engineer Thirumurugan Arumugam. | 2025-07-15T05:11:34.685108
Final EOWR_Diyina_UZ-046_R_signed.pdf | Other Group | pdf | ['08/05/2022', '1-13/16', '22/04/2022'] | ['Well ID', 'WELL ACCESS', 'Well Cost', 'Well Test', 'Well Summary', 'well test', 'Well Name', 'well 10', 'Well Section', 'Well \nUZ', 'Well Access', 'Well testing', 'well 1', 'Well displace'] | The final recap for well UZ-046, operated by ADNOC OFFSHORE UZ and drilled by ADNOC - DRILLING, details workover and well access operations conducted from April 22, 2022, to May 8, 2022, using a CaCl2 brine mud system over an interval of 10,390 feet, with a total mud cost of $63,602.12. Key operations included pressure testing, injectivity tests, cement plug installations, and wireline operations, with significant activities such as bullheading brine, recovering contaminated fluids, and cutting casing at 6,100 feet. | 2025-07-15T05:11:36.487402
Service Data Contractor Feedback - UZ-046 Diyina.pdf | Contractor Feedback | pdf | ['08-05-2022', '08/05/2022'] | ['well reports', 'well report', 'Well Name'] | The document "Service Data Contractor Feedback - UZ-046 Diyina.pdf" details the drilling fluids operations for well UZ-046 on the Diyina rig, conducted by PPC on 08-05-2022, noting no deficiencies in mud chemicals, engineering service, lab equipment, or report submission, and achieving a final score of 100. The actual total volume of 10.2 ppg Inhibited CaCl2 Brine handled was 2917 bbl, compared to the planned 4250 bbl, resulting in a volume ratio of 0.69%. | 2025-07-15T05:11:37.923389
DF Contractor Feedback Form_Database_up to UZ-046.pdf | Contractor Feedback | pdf | ['11/5/2022'] | ['Well Date', 'Well Feedback', 'Well Name'] | The Drilling Fluids Well Feedback Form for well UZ-046, spud on 22.04.2022 and completed on 08.05.2022 by rig DIYINA and service company PETROCHEM, details the use of a 10.2 ppg CaCl2 brine fluid system with no observed losses and a significant cost variance, with actual chemical costs at $63,602.12 compared to the planned $131,743.27. The form was signed by Sigit Kustanto on 12.05.2022. | 2025-07-15T05:11:39.747316
Service Data Contractor Feedback - UZ-046 Diyina.docx | Contractor Feedback | docx | ['08-05-2022', '08/05/2022'] | ['well reports', 'well report', 'Well Name'] | On May 8, 2022, at well UZ-046 on the Diyina rig, PPC provided drilling fluids services with no deficiencies observed in mud chemicals, engineering support, lab equipment, or report submissions, achieving a perfect Fluids Business Support Index score. The actual total volume of 10.2 ppg Inhibited CaCl2 Brine handled was 2917 bbl, with a volume ratio of 0.69%. | 2025-07-15T05:11:40.808923
PPC Operational Risk Asssetment.pdf | Risk Assessment and Hazard Analysis | pdf | ['08/30/2020', '09/01/2020', '09/07/2020', '60/40-70'] | ['well Well', 'Well kill', 'Well control', 'well Loss', 'wellbore', 'Wellbore', 'Well Control'] | The PPC Operational Risk Assessment (RA-2020-000007) for Petrochem Performance Chemicals, conducted on 08/30/2020 and last modified on 09/07/2020, evaluates hazards and risks associated with offshore drilling fluids, including chemical exposure, lifting techniques, chemical spills, and slips, trips, and falls, with initial risk ratings ranging from 4 to 6 and residual risk ratings reduced to 2 after implementing control measures. | 2025-07-15T05:11:42.218373
Hydraulic Report# 46_ULP-407_14_Feb_2018.pdf | Hydraulic Summary | pdf | ['2/14/2018', '21/12/17'] | ['Well ID', 'Well name'] | The Hydraulic Report #46 for well ULP-407 at Umm Lulu field, dated February 14, 2018, details drilling operations conducted by ADNOC-OFFSHORE with key data including a total depth of 13,948 ft MD and 11,400 ft TVD, and various pressure losses and flow rates recorded during the operation. The report includes specific measurements such as a bit size of 10.5 inches and a mud weight of 14.1 lb/gal, with detailed hydraulic and rheological properties noted throughout the drilling process. | 2025-07-15T05:11:43.814642
Hydraulic Report# 45_ULP-407_13_Feb_2018.pdf | Hydraulic Summary | pdf | ['2/13/2018', '21/12/17'] | ['Well ID', 'Well name'] | The Hydraulic Report #45 for well ULP-407 at Umm Lulu field, dated February 13, 2018, details drilling operations conducted by ADNOC-OFFSHORE with a spud date of December 21, 2017, reaching a measured depth (MD) of 13,174 ft and true vertical depth (TVD) of 13,174 ft. The report includes detailed data on mud properties, pressure losses, and flow rates, with specific measurements such as a bit size of 6.000 inches and a total circulation time of 02:36:33. | 2025-07-15T05:11:45.437634
Beynouna-UZ-029-Workover Fluids Program.pdf | Mud Program | pdf | ['4/10/2014', '6/23/2016'] | ['well is', 'well and', 'well bore', 'WELL SUMMARY', 'Well Objectives', 'Well Drawing', 'Well Program', 'Well Plan', 'WELL PROGRAM', 'Well Summary', 'Well Status', 'Well History', 'well temperature', 'well within', 'wellbore', 'well control', 'Well is', 'well \n0', 'well back', 'well \nAH', 'well \ntemperature', 'well was', 'well mention'] | The document "Beynouna-UZ-029-Workover Fluids Program.pdf" outlines the drilling fluids program for the permanent plug and abandonment of well UZ-029, with key operations and approvals dated February 4, 2020, involving personnel such as Alexey Chernyshev and Sheldon Seals from ADNOC DFE. | 2025-07-15T05:11:46.580748
Beynouna-UZ-029 - One Page Summary Final.pdf | Hydraulic Summary | pdf | [] | ['Well is', 'WELL DATA', 'well and', 'well back', 'Well Operations', 'well was', 'WELL OBJECTIVE', 'well mention', 'WELL HISTORY'] | The workover program for well UZ029 at Upper Zakum (UZ) involves permanently abandoning the well, which was originally drilled in December 1978 and has undergone multiple operations, including sidetracking in June 2006 and recompletion in October 2008. The current operation, budgeted at $5,399,402 for 50 days, includes removing existing completions, cutting and recovering casing, and ensuring all annuli are filled with cement before securing the well and preparing for the rig move to the next location. | 2025-07-15T05:11:47.781803
HydraulicSummary at 12158 ft 175 FPH.pdf | Hydraulic Summary | pdf | [] | ['Well\nZK-411', 'Well Function', 'Well Profile', 'well\nOperator', 'Well Type', 'Well Construction', 'Well Pad', 'Well\n883'] | The water injection well ZK-411, operated by ADNOC Offshore and drilled by Shelf Drilling using the HIGH ISLAND VII rig, reached a depth of 12,158 ft on February 28, 2021, with a horizontal profile and utilized RDF NAF mud. | 2025-07-15T05:11:48.577132
ZK-411_11 ppg RDF NAF Drilling at TD_ Low Rhelogy.pdf | Other Group | pdf | [] | ['Well\nZK-411', 'Well Function', 'Well Profile', 'well\nOperator', 'Well Type', 'Well Construction', 'Well\n1455', 'Well Pad'] | The document details the drilling operations for water injection well ZK-411, operated by ADNOC Offshore and drilled by Shelf Drilling on the HIGH ISLAND VII rig at the Lower Zakum oil field, reaching a total depth of 20,300 ft with an 8.5-inch hole size using RDF NAF mud at 11 ppg, completed on July 28, 2021. | 2025-07-15T05:11:49.895734
HydraulicSummary at 12158 ft 125 FPH.pdf | Hydraulic Summary | pdf | [] | ['Well\nZK-411', 'Well Function', 'Well Profile', 'well\nOperator', 'Well Type', 'Well Construction', 'Well Pad', 'Well\n883'] | The document details the hydraulic summary for water injection well ZK-411, operated by ADNOC Offshore and drilled by Shelf Drilling on the HIGH ISLAND VII rig, reaching a depth of 12,158 ft on February 28, 2021, with a rate of penetration of 125 ft/h and using RDF NAF mud. The well, located on pad ZK-307 in the Lower Zakum oil field, features an 8.5-inch hole size and a horizontal profile. | 2025-07-15T05:11:51.369566
ZK-411_9 ppg RDF NAF Drilling at TD_ High Rhelogy.pdf | Other Group | pdf | [] | ['Well\nZK-411', 'Well Function', 'Well Profile', 'well\nOperator', 'Well Type', 'Well Construction', 'Well\n1455', 'Well Pad'] | The document details the drilling operations for water injection well ZK-411, operated by ADNOC Offshore and drilled by Shelf Drilling on the HIGH ISLAND VII rig at the Lower Zakum oil field, reaching a total depth of 20,300 ft with an 8.5-inch hole size using RDF NAF mud on July 28, 2021. Key parameters include a mud weight of 9 ppg, a rate of penetration of 130 ft/h, and various pressure and flow rate measurements. | 2025-07-15T05:11:52.878665
HydraulicSummary at 12158 ft 200 FPH.pdf | Hydraulic Summary | pdf | [] | ['Well\nZK-411', 'Well Function', 'Well Profile', 'well\nOperator', 'Well Type', 'Well Construction', 'Well Pad', 'Well\n883'] | Well ZK-411, a water injection well operated by ADNOC Offshore and drilled by Shelf Drilling, reached a depth of 12,158 ft on February 28, 2021, using an 8.5-inch hole size and RDF NAF mud type, with a drilling rate of 200 ft/h and a flow rate of 504 gal/min. | 2025-07-15T05:11:54.406571
HydraulicSummary at 14880 ft.pdf | Hydraulic Summary | pdf | [] | ['Well\nZK-411', 'Well Function', 'Well Profile', 'Well\n1074', 'well\nOperator', 'Well Type', 'Well Construction', 'Well Pad'] | Well ZK-411, a water injection well operated by ADNOC Offshore and drilled by Shelf Drilling, reached a depth of 14,880 ft on March 2, 2021, using an 8.5-inch hole size and RDF NAF mud type in the Lower Zakum oil field. The well, located on pad ZK-307 and drilled with the HIGH ISLAND VII rig, features a horizontal profile and various detailed hydraulic and mud properties. | 2025-07-15T05:11:55.586957
ZK-411_10 ppg RDF NAF Drilling at TD_ Low Rhelogy.pdf | Other Group | pdf | [] | ['Well\nZK-411', 'Well Function', 'Well Profile', 'well\nOperator', 'Well Type', 'Well Construction', 'Well\n1455', 'Well Pad'] | The water injection well ZK-411, operated by ADNOC Offshore and drilled by Shelf Drilling on the HIGH ISLAND VII rig, reached a total depth of 20,300 ft on July 28, 2021, using 10 ppg RDF NAF mud. The well, located on well pad ZK-307 in the Lower Zakum oil field, features an 8.5-inch horizontal hole profile. | 2025-07-15T05:11:58.002147
HydraulicSummary-8820 ft.pdf | Hydraulic Summary | pdf | [] | ['Well\nZK-411', 'Well\n1347', 'Well Function', 'Well Profile', 'well\nOperator', 'Well Type', 'Well Construction', 'Well Pad'] | The document details the operations of water injection well ZK-411, operated by ADNOC Offshore and drilled by Shelf Drilling on well pad ZK-307 in the Lower Zakum oil field, reaching a depth of 8820 ft with a 12.25-inch hole size using the HIGH ISLAND VII rig and ADNOC Offshore NAF mud type, completed on February 20, 2021. | 2025-07-15T05:12:08.501096
HydraulicSummary at 15610 ft.pdf | Hydraulic Summary | pdf | [] | ['Well\nZK-411', 'Well Function', 'Well Profile', 'well\nOperator', 'Well Type', 'Well\n1125', 'Well Construction', 'Well Pad'] | The document details the hydraulic summary for water injection well ZK-411, operated by ADNOC Offshore and drilled by Shelf Drilling on the HIGH ISLAND VII rig, reaching a depth of 15,610 ft in the Lower Zakum oil field with an 8.5-inch hole size, using RDF NAF mud, on March 2, 2021. Key operational metrics include a mud weight of 7.7 ppg, a flow rate of 505 gal/min, and a standpipe pressure of 2837.6 psi. | 2025-07-15T05:12:09.930891
ZK-411_8 ppg RDF NAF Drilling at TD_ High Rhelogy.pdf | Other Group | pdf | [] | ['Well\nZK-411', 'Well Function', 'Well Profile', 'well\nOperator', 'Well Type', 'Well Construction', 'Well\n1455', 'Well Pad'] | The document details the drilling operations for water injection well ZK-411, operated by ADNOC Offshore and drilled by Shelf Drilling on the HIGH ISLAND VII rig at the Lower Zakum oil field, reaching a total depth of 20,300 ft with an 8.5-inch hole size using RDF NAF mud on July 28, 2021. Key parameters include a mud weight of 8 ppg, a drilling rate of 130 ft/h, and various pressure and flow rate measurements. | 2025-07-15T05:12:11.424951
HydraulicSummary at 13500 ft.pdf | Hydraulic Summary | pdf | [] | ['Well\nZK-411', 'Well\n977', 'Well Function', 'Well Profile', 'well\nOperator', 'Well Type', 'Well Construction', 'Well Pad'] | Well ZK-411, a water injection well operated by ADNOC Offshore and drilled by Shelf Drilling, reached a depth of 13,500 ft on March 1, 2021, using an 8.5-inch hole size and RDF NAF mud type in the Lower Zakum oil field. The well, located on pad ZK-307 and drilled with the HIGH ISLAND VII rig, features a horizontal profile and various detailed hydraulic and mud properties. | 2025-07-15T05:12:12.624442
HydraulicSummary-8215 ft.pdf | Hydraulic Summary | pdf | [] | ['Well\nZK-411', 'Well Function', 'Well Profile', 'well\nOperator', 'Well\n1259', 'Well Type', 'Well Construction', 'Well Pad'] | The document details the hydraulic summary for water injection well ZK-411, operated by ADNOC Offshore and drilled by Shelf Drilling on well pad ZK-307 in the Lower Zakum oil field, reaching a depth of 8215 ft with a 12.25-inch hole size, using the HIGH ISLAND VII rig and ADNOC Offshore NAF mud, with operations conducted on February 19, 2021. | 2025-07-15T05:12:13.954990
HydraulicSummary-9120 ft.pdf | Hydraulic Summary | pdf | [] | ['Well\nZK-411', 'Well Function', 'Well Profile', 'well\nOperator', 'Well Type', 'Well Construction', 'Well Pad', 'Well\n1391'] | Well ZK-411, a water injection well operated by ADNOC Offshore and drilled by Shelf Drilling, reached a depth of 9120 ft on February 19, 2021, using the HIGH ISLAND VII rig at the Lower Zakum oil field. The well, located on pad ZK-307, features a 12.25-inch horizontal hole and utilized ADNOC Offshore NAF mud with a weight of 11.7 ppg. | 2025-07-15T05:12:18.187815
HydraulicSummary-9700 ft.pdf | Hydraulic Summary | pdf | [] | ['Well\nZK-411', 'Well\n1475', 'Well Function', 'Well Profile', 'well\nOperator', 'Well Type', 'Well Construction', 'Well Pad'] | Well ZK-411, a water injection well operated by ADNOC Offshore and drilled by Shelf Drilling using the HIGH ISLAND VII rig, reached a depth of 9700 ft on February 20, 2021, with a 12.25-inch hole size at the Lower Zakum oil field. The well, located on well pad ZK-307, utilized ADNOC Offshore NAF mud with a weight of 11.7 ppg and achieved a drilling rate of 75 ft/h. | 2025-07-15T05:12:28.795701
HydraulicSummary-7600 ft.pdf | Hydraulic Summary | pdf | [] | ['Well\nZK-411', 'Well Function', 'Well Profile', 'well\nOperator', 'Well Type', 'Well Construction', 'Well Pad', 'Well\n1169'] | Well ZK-411, a water injection well operated by ADNOC Offshore and drilled by Shelf Drilling using the HIGH ISLAND VII rig, reached a depth of 7600 ft on February 19, 2021, at the Lower Zakum oil field with a 12.25-inch hole size and utilized ADNOC Offshore NAF mud. | 2025-07-15T05:12:29.834859
6.625 Liner Assembly circ at bottom with RDF.pdf | Other Group | pdf | [] | ['Well\nZK-411', 'Well Function', 'Well Profile', 'well\nOperator', 'Well Type', 'Well\n1434', 'Well Construction', 'Well Pad'] | The document details the liner assembly and circulation operations for water injection well ZK-411, operated by ADNOC Offshore and drilled by Shelf Drilling on the HIGH ISLAND VII rig at the Lower Zakum oil field, with a total depth of 20,000 ft and using RDF NAF mud, completed on March 17, 2021. | 2025-07-15T05:12:34.784614
HydraulicSummary at 12158 ft 100 FPH.pdf | Hydraulic Summary | pdf | [] | ['Well\nZK-411', 'Well Function', 'Well Profile', 'well\nOperator', 'Well Type', 'Well Construction', 'Well Pad', 'Well\n883'] | The document details the hydraulic summary for water injection well ZK-411, operated by ADNOC Offshore, drilled by Shelf Drilling on the HIGH ISLAND VII rig at the Lower Zakum oil field, reaching a depth of 12,158 ft with an 8.5-inch hole size on February 28, 2021. The well, located on pad ZK-307, utilized RDF NAF mud with a drilling rate of 100 ft/h and a flow rate of 504 gal/min. | 2025-07-15T05:12:36.407090
ZK-411_10 ppg RDF NAF Drilling at TD_ High Rhelogy.pdf | Other Group | pdf | [] | ['Well\nZK-411', 'Well Function', 'Well Profile', 'well\nOperator', 'Well Type', 'Well Construction', 'Well\n1455', 'Well Pad'] | The document details the drilling operations for water injection well ZK-411, operated by ADNOC Offshore and drilled by Shelf Drilling on the HIGH ISLAND VII rig at the Lower Zakum oil field, reaching a total depth of 20,300 ft with an 8.5-inch hole size using RDF NAF mud at 10 ppg, completed on Wednesday, July 28, 2021. | 2025-07-15T05:12:39.576043
ZK-411_11 ppg RDF NAF Drilling at TD_ High Rhelogy.pdf | Other Group | pdf | [] | ['Well\nZK-411', 'Well Function', 'Well Profile', 'well\nOperator', 'Well Type', 'Well Construction', 'Well\n1455', 'Well Pad'] | The document details the drilling operations for water injection well ZK-411, operated by ADNOC Offshore and drilled by Shelf Drilling on the HIGH ISLAND VII rig at the Lower Zakum oil field, reaching a total depth of 20,300 ft with an 8.5-inch hole size using RDF NAF mud on July 28, 2021. Key operational parameters include a mud weight of 11 ppg, a rate of penetration of 130 ft/h, and a flow rate of 500 gal/min. | 2025-07-15T05:12:42.062410
HydraulicSummary-9572 ft.pdf | Hydraulic Summary | pdf | [] | ['Well\nZK-411', 'Well Function', 'Well Profile', 'well\nOperator', 'Well Type', 'Well Construction', 'Well Pad', 'Well\n1457'] | Well ZK-411, a water injection well operated by ADNOC Offshore and drilled by Shelf Drilling on well pad ZK-307 in the Lower Zakum oil field, reached a horizontal hole depth of 9572 ft using a 12.25 in bit and ADNOC Offshore NAF mud, with operations conducted on February 20, 2021. | 2025-07-15T05:12:42.990035
HydraulicSummary at 12158 ft 150 FPH.pdf | Hydraulic Summary | pdf | [] | ['Well\nZK-411', 'Well Function', 'Well Profile', 'well\nOperator', 'Well Type', 'Well Construction', 'Well Pad', 'Well\n883'] | The document details the hydraulic summary for water injection well ZK-411, operated by ADNOC Offshore and drilled by Shelf Drilling on well pad ZK-307 in the Lower Zakum oil field, reaching a depth of 12,158 ft with an 8.5-inch hole size using RDF NAF mud, with operations conducted on February 28, 2021. The drilling achieved a rate of penetration (ROP) of 150 ft/h, with a flow rate of 504 gal/min and a standpipe pressure of 2637.9 psi, utilizing the HIGH ISLAND VII rig. | 2025-07-15T05:12:44.714229
HydraulicSummary at 6990.pdf | Hydraulic Summary | pdf | [] | ['Well\nZK-411', 'Well Function', 'Well Profile', 'well\nOperator', 'Well Type', 'Well Construction', 'Well Pad', 'Well\n1080'] | The document details the hydraulic summary for water injection well ZK-411, operated by ADNOC Offshore and drilled by Shelf Drilling on well pad ZK-307 in the Lower Zakum oil field, reaching a depth of 6990 ft with a 12.25-inch hole size, using the HIGH ISLAND VII rig and ADNOC Offshore NAF mud type, with operations conducted on February 18, 2021. | 2025-07-15T05:12:46.065185
ZK-411_9 ppg RDF NAF Drilling at TD_ Low Rhelogy.pdf | Other Group | pdf | [] | ['Well\nZK-411', 'Well Function', 'Well Profile', 'well\nOperator', 'Well Type', 'Well Construction', 'Well\n1455', 'Well Pad'] | The document details the drilling operations for water injection well ZK-411, operated by ADNOC Offshore and drilled by Shelf Drilling on the HIGH ISLAND VII rig at the Lower Zakum oil field, reaching a total depth of 20,300 ft with an 8.5-inch hole size using 9 ppg RDF NAF mud, completed on July 28, 2021. | 2025-07-15T05:12:47.370030
VirtualDrilling.pdf | Other Group | pdf | ['7/28/2021'] | ['well\nRig', 'Wellbore', 'Well Hydraulics', 'Well Pad'] | On July 28, 2021, Petrochem Performance Chemicals Ltd. reported on the development operations of the horizontal water injection well ZK-411, located on well pad ZK-307 in the Lower Zakum oil field, operated by ADNOC Offshore and drilled by Shelf Drilling using the HIGH ISLAND VII jack-up rig. The well reached a measured depth of 20,300 ft and a true vertical depth of 8,796.86 ft, with a maximum standpipe pressure of 4,000 psi and a pump output per stroke of 0.139 bbl. | 2025-07-15T05:12:49.964170
6.625 Liner Assembly Surj report with RDF.pdf | Other Group | pdf | [] | ['Well\nZK-411', 'Well Function', 'Well Profile', 'well\nOperator', 'Well Type', 'Well\n1434', 'Well Construction', 'Well Pad'] | The document details the 6.625 liner assembly for water injection well ZK-411, operated by ADNOC Offshore at the Lower Zakum oil field, with a hole depth of 20,000 ft and an 8.5-inch hole size, conducted by Shelf Drilling using the HIGH ISLAND VII rig on March 17, 2021. The well, located on pad ZK-307, utilized RDF NAF mud with specific properties and detailed pressure and hydraulic measurements. | 2025-07-15T05:12:51.386633
Al Beynounah - UZ-029 - Engineering Ticket 2.2.pdf | Engineering Tickets | pdf | ['16/02/2020', '29-02-2020', '29/02/2020'] | ['well site'] | The document "Al Beynounah - UZ-029 - Engineering Ticket 2.2.pdf" is a Field Personnel Service Quality Assessment for Syarif A Bachmid, a Drilling Fluids Engineer, evaluating his performance at ADNOC's UZ-029 well from 16/02/2020 to 29/02/2020. The assessment covers various criteria including safety, professional skills, personal skills, logistic skills, and home office support, with feedback intended for internal use by Petrochem. | 2025-07-15T05:12:58.948523
Al Beynounah - UZ-029 - Engineering Ticket 3.pdf | Engineering Tickets | pdf | [] | ['well site', 'WELL NO'] | The document "Al Beynounah - UZ-029 - Engineering Ticket 3" details the provision of Lead MWD engineer services by Petrochem Performance Chemicals Limited for ADNOC at well 112-29 on Rig Banouna from March 1, 2020, to March 16, 2020, totaling 16 days. The service quality assessment, completed by company representative Yasir Bajer, rated the performance of Drilling Fluids Engineer Syarif A. Bachmid as consistently exceeding expectations in all categories. | 2025-07-15T05:13:11.388233
Al Beynounah - UZ-029 - Engineering Ticket 4.1.pdf | Engineering Tickets | pdf | ['17-3-2020', '19-3-2020', '20-3-2020', '31-3-2020'] | ['WELL NO'] | The document details engineering service tickets for Petrochem Performance Chemicals Limited L.L.C. on ADNOC Offshore's Beynouna rig, specifically for wells UZ-29 and UZ-129, with services provided by Senior Drilling Fluids Engineer Mohamed Tawfik from March 17-19, 2020 (3 days) for UZ-29, and March 20-31, 2020 (12 days) for UZ-129. | 2025-07-15T05:13:16.329205
Al Beynounah - UZ-029 - Engineering Ticket 1.2.pdf | Engineering Tickets | pdf | ['12/02/2020', '15/02/2020', '29-02-2020'] | ['well site'] | The document "Al Beynounah - UZ-029 - Engineering Ticket 1.2" details a Field Personnel Service Quality Assessment for Drilling Fluids Engineer Andrey Ulyashev, who worked at ADNOC/UZ-029 from 12/02/2020 to 15/02/2020. The assessment, completed on 29/02/2020, rated Ulyashev's performance highly, with most criteria marked as "Always exceeds expectations." | 2025-07-15T05:13:24.501815
Al Beynounah - UZ-029 - Engineering Ticket 4.2.pdf | Engineering Tickets | pdf | ['17/03/2020', '19/03/2020', '31-03-2020'] | ['well site'] | The document "Al Beynounah - UZ-029 - Engineering Ticket 4.2.pdf" details a Field Personnel Service Quality Assessment for Drilling Fluids Engineer Mohamed Tawfik, conducted at ADNOC/UZ-29 from 17/03/2020 to 19/03/2020, with the assessment completed on 31/03/2020. The evaluation covers various performance criteria, with most ratings indicating that the engineer "Exceeds expectations some of the time" and one rating of "Always exceeds expectations" in personal skills. | 2025-07-15T05:13:32.482031
Al Beynounah - UZ-029 - Engineering Ticket 1.1.pdf | Engineering Tickets | pdf | ['12-02-2020', '15-02-2020'] | ['WELL NO'] | The document "Al Beynounah - UZ-029 - Engineering Ticket 1.1" details engineering services provided by PETROCHEM for ADNOC on well UZ-029, with lead mud engineering services conducted from February 12, 2020, to February 15, 2020, totaling 3 days. The PETROCHEM representative was Ulyashev A. | 2025-07-15T05:13:36.219906
Al Beynounah - UZ-029 - Engineering Ticket 2.1.pdf | Engineering Tickets | pdf | ['16-02-2020', '29-02-2020'] | ['WELL NO'] | The document "Al Beynounah - UZ-029 - Engineering Ticket 2.1" details Petrochem Performance Chemicals Limited L.L.C.'s engineering service ticket AB-1845 for lead mud engineering services provided to ADNOC on Rig Beynouna, Well No. Uz-029, from February 16, 2020, to February 29, 2020, spanning a total of 14 days. | 2025-07-15T05:13:40.146828
Beynouna - UZ-029 - Well Recap.pdf | Well Recap | pdf | ['2/17/2020', '3/19/2020'] | ['Well ID', 'wellhead', 'well UZ-029', 'Well Summary', 'Well \nUZ-29', 'Well Name', 'Well Section'] | The final recap for Well UZ-29, operated by ADNOC Offshore and drilled by ADNOC Drilling International, details workover operations conducted from February 17, 2020, to March 19, 2020, including the use of sea water as the mud system and various subsea drilling and cutting activities. Key operations involved deploying and operating a subsea drilling unit (SDU) and a diamond wire saw (DWS) to cut and remove sections of the 36" conductor, with significant challenges encountered during the process. | 2025-07-15T05:13:42.978618
Hi-ISLD-VII-PPC-DMR-37_05-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/5/2021'] | ['Well ID', 'Well Cost', 'Well At', 'well at', 'Well name'] | The document is a Daily Mud Report for the well ZK-411 in the Zakum field, operated by ADNOC Offshore, dated March 5, 2021, detailing drilling operations and mud properties at a depth of 17,318 ft with specific circulation and solids control activities. The report includes data on mud weight, pump efficiency, and the status of cutting skips, with engineers Mohamed Tawfik and Arshad Mehmood overseeing the operations. | 2025-07-15T05:13:44.643155
Hi-ISLD-VII-PPC-DMR-53_21-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/21/2021'] | ['Well ID', 'Well name', 'well \ncontrol', 'Well Cost'] | On March 21, 2021, operations for well ZK-411 in Abu Dhabi, United Arab Emirates, included running in hole (RIH) with an 8 1/2" RSS BHA from 163 ft to 14043 ft, performing circulation and reaming activities, and monitoring mud returns, with a total depth reached of 17318 ft. Key activities also involved loading radioactive sources in LWD tools, conducting shallow tests, and managing cutting skips, with 78 skips sent to the island and 136 skips in total. | 2025-07-15T05:13:46.085464
Hi-ISLD-VII-PPC-DMR-15_11-Feb-2021.pdf | Other Group | pdf | ['2/11/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well Cost'] | The document "Hi-ISLD-VII-PPC-DMR-15_11-Feb-2021.pdf" details the daily mud report for the well ZK-411 in the Zakum field, Abu Dhabi, operated by ADNOC Offshore, covering operations on 28/01/21, including drilling activities from 4947 ft to 5440 ft with specific parameters such as 1050 gpm flow rate and 1800-2100 psi pressure. Key activities included troubleshooting lost MWD signals, pumping high-viscosity pills, and preparing for a cement job, with no obstructions encountered while pulling out of the hole from 5440 ft to 1871 ft. | 2025-07-15T05:13:47.958575
Hi-ISLD-VII-PPC-DMR-56_24-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/24/2021'] | ['Well ID', 'Well name', 'well control', 'Well Cost'] | On January 28, 2021, ADNOC Offshore conducted operations on well ZK-411 at Zakum field, utilizing the HI-ISLAND VII rig by SHELF Drilling, including troubleshooting MWD/LWD tools, performing shallow tests, and running the 8 1/2" RSS BHA to various depths, with significant activities such as filling and breaking circulation, and servicing the TDS. | 2025-07-15T05:13:49.002447
Hi-ISLD-VII-PPC-DMR-60_28-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/28/2021'] | ['Well ID', 'Well Cost', 'well on', 'well and', 'Well name'] | On January 28, 2021, ADNOC Offshore conducted operations on well ZK-411 in the Zakum field, Abu Dhabi, utilizing the HI-ISLAND VII rig by SHELF Drilling, with significant activities including a pressure point survey at various depths and POOH from 15,345 ft to 8,300 ft, noting dynamic losses of 12 BPH and no static loss. | 2025-07-15T05:13:50.361021
Hi-ISLD-VII-PPC-DMR-11_07-Feb-2021.pdf | Other Group | pdf | ['2/7/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well Cost'] | The document "Hi-ISLD-VII-PPC-DMR-11_07-Feb-2021.pdf" details the daily mud report for the well ZK-411 in the Zakum field, operated by ADNOC Offshore, with significant drilling activities recorded on 28/01/21, including drilling from 315 ft to 795 ft using a steerable system and receiving 24 MT of Bentonite from ADNOC-227 Vessel. | 2025-07-15T05:13:51.551927
Hi-ISLD-VII-PPC-DMR-49_17-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/17/2021'] | ['Well ID', 'Well Cost', 'Well\nShawn', 'well \ncontrol', 'well at', 'Well\nAbu', 'Well\nSajeev', 'Well name'] | The document "Hi-ISLD-VII-PPC-DMR-49_17-Mar-2021.pdf" details the daily mud report for well ZK-411 in the Zakum field, operated by ADNOC Offshore, with key operations on 28/01/21 and monitoring at 3280 ft due to a crew shortage caused by COVID-19. The report includes specific data on mud properties, bit hydraulics, and solids control equipment, with engineers Mohamed Tawfik and Arshad Mehmood overseeing the operations. | 2025-07-15T05:13:53.099457
Hi-ISLD-VII-PPC-DMR-69_06-April-2021.pdf | Other Group | pdf | ['28/01/21', '4/6/2021'] | ['Well ID', 'Well name', 'Well Cost', 'well to'] | The document "Hi-ISLD-VII-PPC-DMR-69_06-April-2021.pdf" details the daily mud report for the ZK-411 well in the Zakum field, Abu Dhabi, operated by ADNOC Offshore on January 28, 2021, with significant operations including circulation while waiting on weather and backloading NAF to vessel 227. The well reached a depth of 20,300 ft with a mud weight of 7.8 ppg, and the report includes detailed mud properties, solids analysis, and equipment status. | 2025-07-15T05:13:54.733030
Hi-ISLD-VII-PPC-DMR-8_04-Feb-2021.pdf | Other Group | pdf | ['2/4/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well Cost'] | On January 28, 2021, ADNOC Offshore conducted drilling operations on well ZK-411 at the Zakum field in Abu Dhabi, reaching a total depth of 315 feet using water-based mud and various sweeps, with significant activities including running a 30'' conductor to 297 feet and preparing 500 bbl of PHB mud. | 2025-07-15T05:13:56.011271
Hi-ISLD-VII-PPC-DMR-40_08-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/8/2021'] | ['Well ID', 'Well Cost', 'Well At', 'well at', 'Well name'] | On 28/01/21, operations at well ZK-411 in the Zakum field, Abu Dhabi, were suspended due to crew shortages caused by COVID-19, with monitoring and circulation continuing at the 9 5/8" casing shoe; the report includes detailed mud properties and solids control data. | 2025-07-15T05:13:57.061066
Hi-ISLD-VII-PPC-DMR-34_02-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/2/2021'] | ['Well ID', 'Well name', 'Well Cost'] | The document "Hi-ISLD-VII-PPC-DMR-34_02-Mar-2021.pdf" details drilling operations for well ZK-411 in Abu Dhabi, United Arab Emirates, on March 2, 2021, including the drilling of an 8 1/2" hole from 14,880 ft to 17,318 ft with specific parameters (500 gpm, 2650-2900 psi, 180-190 RPM, 13-24 K trq, and 10-25 Klb WOB). The report also includes information on mud properties, circulation, and solids control, with 56 cutting skips sent to the island and a total of 136 skips accounted for. | 2025-07-15T05:13:58.960755
Hi-ISLD-VII-PPC-DMR-35_03-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/3/2021'] | ['Well ID', 'Well Cost', 'well at', 'Well At', 'Well name', 'well static'] | The document "Hi-ISLD-VII-PPC-DMR-35_03-Mar-2021.pdf" details the daily mud report for well ZK-411 in the Zakum field, Abu Dhabi, on 28/01/21, including operations such as monitoring the well at the 9 5/8" CSG shoe, reaming from 10570 ft to 10040 ft, and circulating bottom up with no losses reported. The report also includes specific data on mud properties, bit hydraulics, and solids control equipment, with a total depth of 17318 ft and a mud weight reduction from 7.8 ppg to 7.7 ppg. | 2025-07-15T05:14:01.124923
Hi-ISLD-VII-PPC-DMR-19_15-Feb-2021.pdf | Other Group | pdf | ['2/15/2021', '28/01/21'] | ['Well ID', 'Well name', 'wellhead', 'Well Cost'] | On January 28, 2021, ADNOC Offshore conducted operations on well ZK-411 in the Zakum field, Abu Dhabi, utilizing the HI-ISLAND VII rig by SHELF Drilling. Key activities included pressure testing BOPs, running in hole (RIH) with a 12 1/4" RSS BHA to a depth of 3531 ft, and receiving 1450 bbl of 11.2 ppg NAF. | 2025-07-15T05:14:02.798260
Hi-ISLD-VII-PPC-DMR-50_18-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/18/2021'] | ['Well ID', 'Well Cost', 'Well\nShawn', 'well \ncontrol', 'well at', 'Well\nAbu', 'Well\nSajeev', 'Well name'] | The document "Hi-ISLD-VII-PPC-DMR-50_18-Mar-2021.pdf" details the daily mud report for well ZK-411 in the Zakum field, Abu Dhabi, operated by ADNOC Offshore, with significant operations noted on 28/01/21 and 18/03/21. Key activities include monitoring the well at 3280 ft, filling the hole with 5 bbl of mud every 24 hours, and managing cutting skips, with a total of 136 skips recorded. | 2025-07-15T05:14:05.239783
Hi-ISLD-VII-PPC-DMR-51_19-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/19/2021'] | ['Well ID', 'Well Cost', 'Well\nShawn', 'well \ncontrol', 'well at', 'Well\nAbu', 'Well\nSajeev', 'Well name'] | The Daily Mud Report for well ZK-411, operated by ADNOC OFFSHORE UZ and located in Abu Dhabi, was documented on January 28, 2021, with key operations including monitoring the well at 3280 ft and suspending operations due to a crew shortage caused by COVID-19. The report details various mud properties, circulation volumes, and the status of cutting skips, with specific numerical data on mud weights, viscosities, and other drilling parameters. | 2025-07-15T05:14:11.756280
Hi-ISLD-VII-PPC-DMR-14_10-Feb-2021.pdf | Other Group | pdf | ['2/10/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well Cost'] | The document "Hi-ISLD-VII-PPC-DMR-14_10-Feb-2021.pdf" details the daily mud report for the drilling operations on well ZK-411 in the Zakum field, Abu Dhabi, conducted by ADNOC Offshore on January 28, 2021, with significant drilling activities including the continuation of drilling the 16" hole section from 3473 ft to 4947 ft. The report includes detailed mud properties, circulation data, and the use of specific equipment such as the HI-ISLAND VII rig and various mud treatment procedures. | 2025-07-15T05:14:17.524892
Hi-ISLD-VII-PPC-DMR-31_27-Feb-2021.pdf | Other Group | pdf | ['2/27/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well Cost', 'well to'] | The document is a daily mud report for the well ZK-411 in the Zakum field, operated by ADNOC Offshore, detailing operations on 28/01/21, including drilling activities from 10040 ft to 10700 ft and the preparation of 1250 bbl of 7.5 ppg RDF. Key personnel involved were Mohamed Tawfik and Arshad Mehmood, with the rig contractor being Shelf Drilling on the Hi-Island VII rig. | 2025-07-15T05:14:25.210088
Hi-ISLD-VII-PPC-DMR-12_08-Feb-2021.pdf | Other Group | pdf | ['2/8/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well Cost'] | On 28/01/21, ADNOC Offshore conducted drilling operations on well ZK-411 at the UZ Khaled field, utilizing the HI-ISLAND VII rig by SHELF Drilling, progressing from 795 ft to 1961 ft in rotary and slide mode with specific mud treatments and dynamic loss observations. | 2025-07-15T05:14:26.552388
Hi-ISLD-VII-PPC-DMR-26_22-Feb-2021.pdf | Other Group | pdf | ['2/22/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well Cost'] | The document "Hi-ISLD-VII-PPC-DMR-26_22-Feb-2021.pdf" details the daily mud report for the ZK-411 well in the Zakum field, operated by ADNOC Offshore, with significant operations including running casing to 5171 ft and cleaning pits for a cement job on 28/01/21. Key personnel involved were Mohamed Tawfik and Arshad Mehmood, and the report includes detailed mud properties and circulation data. | 2025-07-15T05:14:35.348165
Hi-ISLD-VII-PPC-DMR-58_26-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/26/2021'] | ['Well ID', 'well control', 'Well Cost', 'Well na', 'Well name'] | On 28/01/21, ADNOC Offshore's rig HI-ISLAND VII, operated by SHELF Drilling, continued drilling the ZAKUM well from 19928 ft to 20300 ft, addressing MWD downlink issues and managing dynamic losses of 15-20 bbl/hr. On 26th March 2021, a filter unit operator was onboard, and 850 bbl of base oil and chemicals were received from A-227 to control mud weight and well conditions. | 2025-07-15T05:14:38.918330
Hi-ISLD-VII-PPC-DMR-17_13-Feb-2021.pdf | Other Group | pdf | ['2/13/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well Cost'] | On January 28, 2021, ADNOC Offshore conducted operations on well ZK-411 in the Zakum field, Abu Dhabi, involving the installation of 13 3/8" casing from 2571 ft to 5422 ft, with a cementing job completed using 515 bbl of 15.8 ppg slurry and 20 bbl of fresh water. The total well cost reported was $85,416.76, with cumulative product costs amounting to $60,843.76. | 2025-07-15T05:14:42.360657
Hi-ISLD-VII-PPC-DMR-74_11-April-2021.pdf | Other Group | pdf | ['28/01/21', '4/11/2021'] | ['Well ID', 'Well name', 'Well Cost'] | The document "Hi-ISLD-VII-PPC-DMR-74_11-April-2021.pdf" details the daily mud report for well ZK-411 in the Zakum field, Abu Dhabi, operated by ADNOC Offshore, with significant operations including the landing of the upper completion and testing of the TH on April 11, 2021. The report also notes the removal of a 13 5/8" x 10K PSI BOP stack and the installation of a 4 1/16" 5k FMC Christmas tree, with a total well cost of $2,229,560.81. | 2025-07-15T05:14:44.182375
Hi-ISLD-VII-PPC-DMR-16_12-Feb-2021.pdf | Other Group | pdf | ['2/12/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well \nstatic', 'Well Cost'] | The document "Hi-ISLD-VII-PPC-DMR-16_12-Feb-2021.pdf" details the daily mud report for well ZK-411 in the Zakum field, Abu Dhabi, operated by ADNOC Offshore, with significant operations including running 13 3/8" casing to 2571 ft on 28/01/21 and noting a loss rate of 40-50 bph. The report also includes detailed mud properties, circulation data, and a cumulative product cost of $60,843.76. | 2025-07-15T05:14:45.606059
Hi-ISLD-VII-PPC-DMR-39_07-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/7/2021'] | ['Well ID', 'Well Cost', 'Well At', 'well at', 'Well name'] | The document "Hi-ISLD-VII-PPC-DMR-39_07-Mar-2021.pdf" is a Daily Mud Report for the well ZK-411 operated by ADNOC Offshore in the Zakum field, Abu Dhabi, dated 28/01/21, detailing drilling operations, mud properties, and circulation activities at a depth of 17,318 ft with engineers Mohamed Tawfik and Arshad Mehmood. | 2025-07-15T05:14:46.817796
Hi-ISLD-VII-PPC-DMR-76_13-April-2021.pdf | Other Group | pdf | ['28/01/21', '4/13/2021'] | ['Well ID', 'Well name', 'Well Cost'] | The document "Hi-ISLD-VII-PPC-DMR-76_13-April-2021.pdf" details the daily mud report for well ZK-411 in the Zakum field, Abu Dhabi, operated by ADNOC Offshore, with significant activities on 28/01/21 and 13/04/21, including preparations for a rig move and backloading chemicals. The well reached a depth of 20,300 ft with a total well cost of $2,234,936.79. | 2025-07-15T05:14:48.427479
Hi-ISLD-VII-PPC-DMR-6_01-Feb-2021.pdf | Other Group | pdf | ['2/2/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well Cost'] | The document is a daily mud report for the well ZK-88/49 located in the Zakum field, Abu Dhabi, operated by ADNOC Offshore, with key activities on 28/01/21 involving waiting on weather to unload spud chemicals and general housekeeping. The report includes detailed mud properties, inventory, and costs, with a cumulative product cost of $4,441.95 and a total well cost of $12,354.95. | 2025-07-15T05:14:49.697811
Hi-ISLD-VII-PPC-DMR-68_05-April-2021.pdf | Other Group | pdf | ['28/01/21', '4/5/2021'] | ['Well ID', 'Well Cost', 'well with', 'Well name', 'well to'] | The document "Hi-ISLD-VII-PPC-DMR-68_05-April-2021.pdf" details the daily mud report for well ZK-411 in the Zakum field, Abu Dhabi, operated by ADNOC Offshore, with significant operations noted on 28/01/21 and 04/05/21, including circulation activities and mud properties maintenance while waiting on weather. The well reached a depth of 20,300 ft with specific mud treatments and equipment usage documented, including the use of centrifuges and cutting skips management. | 2025-07-15T05:14:51.612462
Hi-ISLD-VII-PPC-DMR-3_30-1-2021.pdf | Other Group | pdf | ['1/30/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well Cost'] | On January 28, 2021, ADNOC Offshore completed preload operations on the HI-ISLAND VII rig, jacking it up to a 53 ft air gap and securing it, with final leg penetration checked by divers. The rig was centered over well ZK-88/49, and various installations and equipment offloading were conducted, including receiving 1100 barrels of drill water via MV Mac Kestrel. | 2025-07-15T05:14:52.994247
Hi-ISLD-VII-PPC-DMR-22_18-Feb-2021.pdf | Other Group | pdf | ['2/18/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well Cost'] | On February 18, 2021, operations on well ZK-411 in the Zakum field, Abu Dhabi, involved drilling a 12.25" hole from 6990 ft to 8215 ft with RSS, performing a wiper trip, and treating the active system with various chemicals. The report also noted the receipt of 23 empty skips from BL-313 and the change of shaker screens to API 200 on Shaker #1 and API 170 on Shakers #2 and #3. | 2025-07-15T05:14:55.049961
Hi-ISLD-VII-PPC-DMR-9_05-Feb-2021.pdf | Other Group | pdf | ['2/5/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well Cost'] | The document "Hi-ISLD-VII-PPC-DMR-9_05-Feb-2021.pdf" details the daily mud report for the ZK-411 well in the Zakum field, Abu Dhabi, operated by ADNOC Offshore, with significant operations including the arrival of the BSS crew on February 5, 2021, and the completion of a conductor cementing job. | 2025-07-15T05:14:56.372290
Hi-ISLD-VII-PPC-DMR-29_25-Feb-2021.pdf | Other Group | pdf | ['2/25/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well Cost'] | On February 25, 2021, operations at well ZK-411 in Abu Dhabi, United Arab Emirates, included changing BOP rams, running in hole (RIH) with 5 1/2" HWDP to 1215 ft, and then with 5" DP to 6843 ft, followed by pulling out of hole (POOH) to 2590 ft. Additionally, 400 bbl of NAF was backloaded onto the A-227 supply vessel, and various materials were received from the Mac Kestrel supply vessel. | 2025-07-15T05:14:58.078037
Hi-ISLD-VII-PPC-DMR-38_06-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/6/2021'] | ['Well ID', 'Well Cost', 'Well At', 'well at', 'Well name'] | The daily mud report for well ZK-411 in the Zakum field, operated by ADNOC Offshore, details operations on 28/01/21, including a total depth of 17,318 ft and specific mud properties and circulation activities. | 2025-07-15T05:14:58.951780
Hi-ISLD-VII-PPC-DMR-66_03-April-2021.pdf | Other Group | pdf | ['28/01/21', '4/3/2021'] | ['Well ID', 'Well name', 'Well Cost'] | On January 28, 2021, ADNOC Offshore conducted operations on the Zakum field well, HI-ISLAND VII, reaching a depth of 20,300 ft with significant activities including freeing a 6 5/8" liner at 17,405 ft and managing dynamic losses of 2-3 bbl/hr. | 2025-07-15T05:14:59.928642
Hi-ISLD-VII-PPC-DMR-24_20-Feb-2021.pdf | Other Group | pdf | ['2/20/2021', '28/01/21'] | ['Well ID', 'Well Cost', 'well on', 'well \nstatic', 'Well name'] | On February 20, 2021, drilling operations for well ZK-411 in the Zakum field, Abu Dhabi, continued with the drilling of a 12.25" hole from 9572 ft to 10050 ft, including troubleshooting MWD issues and performing circulation and cleaning activities. | 2025-07-15T05:15:00.938655
Hi-ISLD-VII-PPC-DMR-67_04-April-2021.pdf | Other Group | pdf | ['28/01/21', '4/4/2021'] | ['Well ID', 'Well name', 'Well Cost'] | On January 28, 2021, ADNOC Offshore conducted operations at the Zakum field using the HI-ISLAND VII rig, focusing on washing the hole from 17,382 ft to 20,300 ft and setting a 6 5/8" lower completion at 20,285 ft, with various circulation and pressure activities detailed throughout the report. | 2025-07-15T05:15:03.101851
Hi-ISLD-VII-PPC-DMR-73_10-April-2021.pdf | Other Group | pdf | ['28/01/21', '4/10/2021'] | ['well on', 'Well ID', 'Well name', 'Well Cost'] | On April 10, 2021, the well ZK-411 in the Zakum field, Abu Dhabi, UAE, operated by ADNOC Offshore, reached a measured depth of 20,300 ft and a true vertical depth of 10,456.47 ft, with operations including running the upper completion on 4 1/2" tubing from 1107 ft to 9609 ft. | 2025-07-15T05:15:05.491028
Hi-ISLD-VII-PPC-DMR-61_29-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/29/2021'] | ['well on', 'Well ID', 'Well name', 'Well Cost'] | On January 28, 2021, ADNOC Offshore conducted operations on well ZK-411 located in the Zakum field, Abu Dhabi, with significant activities including running in hole (RIH) with 5 1/2" drill pipe from 8300 ft to 9850 ft, pulling out of hole (POOH) to surface, and monitoring well displacement, culminating in a total depth of 20,300 ft as of March 29, 2021. | 2025-07-15T05:15:12.367177
Hi-ISLD-VII-PPC-DMR-21_17-Feb-2021.pdf | Other Group | pdf | ['2/17/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well Cost'] | On January 28, 2021, ADNOC Offshore conducted drilling operations on well ZK-411 at the Zakum field, reaching a depth of 6990 ft with a 12.25" hole using a Halliburton insert roller cone bit, and treated the mud system with various additives to maintain drilling efficiency. | 2025-07-15T05:15:17.418958
Hi-ISLD-VII-PPC-DMR-23_19-Feb-2021.pdf | Other Group | pdf | ['2/19/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well Cost'] | On 28/01/21, drilling operations for well ZK-411 in the Zakum field, Abu Dhabi, continued with the Hi-Island VII rig, drilling a 12.25" hole from 8215 ft to 9572 ft, while addressing mud pump issues and treating the active system with various additives. | 2025-07-15T05:15:25.667617
Hi-ISLD-VII-PPC-DMR-30_26-Feb-2021.pdf | Other Group | pdf | ['2/26/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well Cost'] | On 28/01/21, ADNOC Offshore conducted operations on well ZK-411 in the Zakum field, reaching a depth of 10,050 ft, with significant activities including running in hole (RIH) and testing MWD tools at various depths, and a cumulative product cost of $202,169.02. | 2025-07-15T05:15:26.719387
Hi-ISLD-VII-PPC-DMR-43_11-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/11/2021'] | ['Well ID', 'Well Cost', 'Well\nShawn', 'well at', 'Well\nAbu', 'Well\nSajeev', 'Well name'] | The document "Hi-ISLD-VII-PPC-DMR-43_11-Mar-2021.pdf" details the daily mud report for the ZK-411 well in the Zakum field, Abu Dhabi, operated by ADNOC Offshore, with significant operations on 28/01/21 and 11/03/21, including monitoring the well at 3280 ft and suspending operations due to a crew shortage caused by COVID-19. The report includes detailed mud properties, bit hydraulics, and solids control equipment, with a cumulative product cost of $778,906.66 and a total well cost of $1,432,476.42. | 2025-07-15T05:15:37.175116
Hi-ISLD-VII-PPC-DMR-18_14-Feb-2021.pdf | Other Group | pdf | ['2/14/2021', '28/01/21'] | ['Well ID', 'Well name', 'Wellhead', 'Well Cost'] | The document "Hi-ISLD-VII-PPC-DMR-18_14-Feb-2021.pdf" details the daily mud report for well ZK-411 in the Zakum field, Abu Dhabi, operated by ADNOC Offshore, with key operations including the installation and pressure testing of the wellhead and BOPs on 28/01/21, and the continuation of R/D 13 3/8" CSG equipment on 14/02/21. The total well cost reported is $87,072.76, with cumulative product costs amounting to $60,843.76. | 2025-07-15T05:15:40.087662
Hi-ISLD-VII-PPC-DMR-64_01-April-2021.pdf | Other Group | pdf | ['28/01/21', '4/1/2021'] | ['well on', 'Well ID', 'Well name', 'Well Cost'] | The document "Hi-ISLD-VII-PPC-DMR-64_01-April-2021.pdf" details the daily mud report for well ZK-411 in the Zakum field, operated by ADNOC Offshore, with key operations including running a 6 5/8" liner from 316 ft to 8057 ft on April 1, 2021, and monitoring well displacement. The report also includes data on mud properties, solids control, and bit hydraulics, with specific measurements such as a hole depth of 20,300 ft and various circulation pressures and volumes. | 2025-07-15T05:15:42.833105
Hi-ISLD-VII-PPC-DMR-33_01-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/1/2021'] | ['Well ID', 'Well name', 'Well Cost'] | The document "Hi-ISLD-VII-PPC-DMR-33_01-Mar-2021.pdf" details drilling operations for well ZK-411 in Abu Dhabi, United Arab Emirates, on March 1, 2021, including the drilling of an 8.5" hole from 12,350 ft to 14,880 ft with specific parameters (500 gpm, 2650-2800 psi, 180-190 RPM, 11-23 K trq, and 10-20 Klb WOB) and various treatments to improve drilling fluid properties. | 2025-07-15T05:15:44.725730
Hi-ISLD-VII-PPC-DMR-10_06-Feb-2021.pdf | Other Group | pdf | ['2/6/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well Cost'] | On February 6, 2021, the daily mud report for well ZK-411 in the Zakum field, operated by ADNOC Offshore, detailed operations including the continuation of N/UP marine riser and diverter, installation of the master bushing, and shallow testing of MWD and motor at various pressures and flow rates. The report also noted the preparation of 1500 bbl PHB mud and the receipt of 500 bbl base oil from vessel A-222. | 2025-07-15T05:15:46.086840
Hi-ISLD-VII-PPC-DMR-4_31-1-2021.pdf | Other Group | pdf | ['1/31/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well Cost'] | On January 31, 2021, operations at well ZK-88/49 in the Zakum field, Abu Dhabi, included offloading 75% of spud equipment, receiving Barite and Bentonite, and conducting load tests on cranes, with activities halted due to weather conditions. | 2025-07-15T05:15:47.158645
Hi-ISLD-VII-PPC-DMR-20_16-Feb-2021.pdf | Other Group | pdf | ['2/16/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well Cost'] | The document "Hi-ISLD-VII-PPC-DMR-20_16-Feb-2021.pdf" details the daily mud report for the ZK-411 well in the Zakum field, operated by ADNOC Offshore, with significant operations occurring on 28/01/21, including drilling from 5270 ft to 5482 ft and various mud treatments. Key personnel include engineers Mohamed Tawfik and Arshad Mehmood, with the report highlighting the use of oil-based mud and specific hydraulic and drilling parameters. | 2025-07-15T05:15:48.766557
Hi-ISLD-VII-PPC-DMR-41_09-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/9/2021'] | ['Well ID', 'Well Cost', 'well at', 'Well At', 'Well\nAbu', 'Well\nSajeev', 'Well name'] | The document "Hi-ISLD-VII-PPC-DMR-41_09-Mar-2021.pdf" reports on well ZK-411 in Abu Dhabi, United Arab Emirates, operated by ADNOC Offshore. Operations were suspended on March 9, 2021, due to crew shortages caused by COVID-19, with the well being monitored at the 9 5/8" casing shoe and the 8.5" RSS/LWD BHA pulled out of the hole at 2877 ft. | 2025-07-15T05:15:50.354772
Hi-ISLD-VII-PPC-DMR-42_10-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/10/2021'] | ['Well ID', 'Well Cost', 'well on', 'Well name', 'Well\nTripping'] | On January 28, 2021, operations at well ZK-411 in the Zakum field, Abu Dhabi, were suspended due to a crew shortage caused by COVID-19, with the RSS/LWD BHA pulled out from 2887 ft to the surface and BOPs pressure tested as per ADNOC's program. | 2025-07-15T05:15:51.437185
Hi-ISLD-VII-PPC-DMR-52_20-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/20/2021'] | ['Well ID', 'Well Cost', 'well \ncontrol', 'well at', 'Well\nAbu', 'Well\nSajeev', 'Well name', 'Well\nTripping'] | The document "Hi-ISLD-VII-PPC-DMR-52_20-Mar-2021.pdf" details operations for well ZK-411 in the Zakum field, Abu Dhabi, with a report date of 28/01/21. Key activities include suspending operations due to COVID-19, monitoring the well at 3280 ft, performing a BOP test, and running in hole with an 8 1/2" RSS/LWD BHA to 82 ft. | 2025-07-15T05:15:54.021842
Hi-ISLD-VII-PPC-DMR-36_04-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/4/2021'] | ['Well ID', 'Well Cost', 'Well At', 'well at', 'Well name'] | The document "Hi-ISLD-VII-PPC-DMR-36_04-Mar-2021.pdf" details operations for well ZK-411 in Abu Dhabi, United Arab Emirates, on March 4, 2021, including the continuation of monitoring at the 9 5/8" casing shoe with no losses reported and the use of a Smith PDC drilling bit at a depth of 17,318 feet. | 2025-07-15T05:15:55.197772
Hi-ISLD-VII-PPC-DMR-55_23-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/23/2021'] | ['Well ID', 'well control', 'Well Cost', 'well on', 'Well static', 'Well name'] | On March 23, 2021, operations at well ZK-411 in Abu Dhabi, United Arab Emirates, included pulling out of hole (POOH) from 10,900 ft to the 9 5/8" shoe at 10,036 ft, changing the Kelly hose, and conducting PCR tests and vaccinations for the drill crew, with the well being monitored on the trip tank and remaining static. | 2025-07-15T05:15:56.542147
Hi-ISLD-VII-PPC-DMR-70_07-April-2021.pdf | Other Group | pdf | ['28/01/21', '4/7/2021'] | ['Well ID', 'Well Cost', 'well on', 'well and', 'well with', 'Well name'] | On January 28, 2021, ADNOC Offshore conducted operations at the Zakum field using the HI-ISLAND VII rig, focusing on displacing well fluids with viscous sea water and performing various cleanout and scraping activities at depths ranging from 9,595 ft to 1,220 ft, with significant observations including 2 BPH losses and the return of 1,300 BBL of good NAF. | 2025-07-15T05:15:57.575696
Hi-ISLD-VII-PPC-DMR-27_23-Feb-2021.pdf | Other Group | pdf | ['2/23/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well Cost'] | On January 28, 2021, ADNOC Offshore conducted operations on well ZK-411 in the Zakum field, Abu Dhabi, involving the continuation of running in hole (RIH) with 9 5/8" casing to 10,036 ft and performing a cementing job with 557 barrels of 14.2 PPG Duraset lead slurry. | 2025-07-15T05:15:59.881393
Hi-ISLD-VII-PPC-DMR-71_08-April-2021.pdf | Other Group | pdf | ['28/01/21', '4/8/2021'] | ['Well ID', 'Well Cost', 'well on', 'well \nabove', 'Well name'] | The document "Hi-ISLD-VII-PPC-DMR-71_08-April-2021.pdf" details the daily mud report for well ZK-411 in the Zakum field, Abu Dhabi, operated by ADNOC Offshore on 28/01/21, including operations such as running in hole (RIH) to 9595 ft with 5" and 5 1/2" drill pipe, and monitoring well losses of 2 BPH. | 2025-07-15T05:16:01.322928
Hi-ISLD-VII-PPC-DMR-25_21-Feb-2021.pdf | Other Group | pdf | ['2/21/2021', '28/01/21'] | ['Well ID', 'Well Cost', 'well on', 'Well name', 'well static'] | The document "Hi-ISLD-VII-PPC-DMR-25_21-Feb-2021.pdf" details the daily mud report for well ZK-411 in the Zakum field, operated by ADNOC Offshore, with key operations on January 28, 2021, including running in hole (RIH) to 10,050 ft and pulling out of hole (POOH) to 89 ft, and treating the active system with base oil. | 2025-07-15T05:16:02.756246
Hi-ISLD-VII-PPC-DMR-7_03-Feb-2021.pdf | Other Group | pdf | ['2/3/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well Cost'] | On January 28, 2021, ADNOC Offshore UZ conducted drilling operations on well ZK-88/49 located in Abu Dhabi, UAE, using the HI-ISLAND VII rig. The team drilled a 36" hole section from 146 ft to 275 ft, utilizing sea water and PHB sweeps, and prepared 500 bbl of PHB mud to maintain surface volume, with a cumulative product cost of $5,897.58 and a total well cost of $14,858.58. | 2025-07-15T05:16:04.293584
Hi-ISLD-VII-PPC-DMR-5_01-Feb-2021.pdf | Other Group | pdf | ['2/1/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well Cost'] | The document "Hi-ISLD-VII-PPC-DMR-5_01-Feb-2021.pdf" details the daily mud report for the ZK-88/49 well operated by ADNOC Offshore on January 28, 2021, with key activities including waiting on weather to unload spud chemicals, conducting load tests on cranes, and mixing 1386 bbl of PHB in tanks using Bentonite and Soda Ash. The total well cost reported was $10,856.95. | 2025-07-15T05:16:05.813715
Hi-ISLD-VII-PPC-DMR-59_27-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/27/2021'] | ['Well ID', 'Well name', 'well control', 'Well Cost'] | The Daily Mud Report for well ZK-411 in the Zakum field, operated by ADNOC Offshore, details operations on 28/01/21, including reaming from 20,300 ft to 17,300 ft with specific parameters (485 GPM, 2280 PSI, 80 RPM) and subsequent POOH to 15,345 ft, with a total of 15/30 pressure points completed. Additionally, a filter unit operator was onboard from 26th March 2021, and the status of cutting skips was documented, with 80 skips sent to the island and a total of 110 skips accounted for. | 2025-07-15T05:16:12.833328
Hi-ISLD-VII-PPC-DMR-54_22-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/22/2021'] | ['Well ID', 'Well Cost', 'well on', 'well \ncontrol', 'Well name'] | On January 28, 2021, operations at the ZAKUM well on HI-ISLAND VII involved reaming from 14,000 ft to 17,318 ft, addressing a tight spot at 15,235 ft, and performing a pressure point survey at various depths, with a final POOH from 17,318 ft to 10,900 ft due to an iCruise RSS issue. The active system was treated with lime and a dilution pill, and 50 MT Microdense and 780 bbl of 9 ppg RDF were prepared for well control. | 2025-07-15T05:16:18.603787
Hi-ISLD-VII-PPC-DMR-63_31-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/31/2021'] | ['Well ID', 'Well name', 'Well Cost'] | The document is a Daily Mud Report for the ZK-411 well in the Zakum field, Abu Dhabi, dated March 31, 2021, detailing operations including the running in hole (RIH) of a 6 5/8 liner to 316 ft and completion of a BOP test. The report also includes data on mud properties, circulation volumes, and solids control equipment, with specific numerical values for various parameters such as depth (20300 ft MD, 10456.47 ft TVD) and mud weight (8.2 lb/gal). | 2025-07-15T05:16:26.435632
Hi-ISLD-VII-PPC-DMR-57_25-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/25/2021'] | ['Well ID', 'Well name', 'well control', 'Well Cost'] | On March 25, 2021, operations at well ZK-411 in Abu Dhabi, United Arab Emirates, involved running an 8 1/2" RSS BHA from 11,520 ft to 17,318 ft, drilling to 18,920 ft, and managing downhole losses of 12-15 bbl/hr, with specific drilling parameters including 480 GPM, 2200-2400 PSI, and 155 RPM. | 2025-07-15T05:16:27.616141
Hi-ISLD-VII-PPC-DMR-75_12-April-2021.pdf | Other Group | pdf | ['28/01/21', '4/12/2021'] | ['Well ID', 'Well name', 'Well Cost'] | On April 12, 2021, operations on well ZK-411 in the Zakum field, Abu Dhabi, UAE, involved preparing for a rig move and pressure testing the Xmas tree, with the well reaching a measured depth of 20,300 feet and a true vertical depth of 10,456.47 feet. | 2025-07-15T05:16:36.669237
Hi-ISLD-VII-PPC-DMR-46_14-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/14/2021'] | ['Well ID', 'Well Cost', 'Well\nShawn', 'well at', 'Well\nAbu', 'Well\nSajeev', 'Well name'] | The document "Hi-ISLD-VII-PPC-DMR-46_14-Mar-2021.pdf" details the daily mud report for well ZK-411 in the Zakum field, Abu Dhabi, operated by ADNOC Offshore, with significant operations noted on 28/01/21 and 14/03/21, including monitoring the well at 3280 ft and receiving 470 bbl of base oil. Operations were suspended due to a crew shortage caused by COVID-19. | 2025-07-15T05:16:40.528708
Hi-ISLD-VII-PPC-DMR-48_16-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/16/2021'] | ['Well ID', 'Well Cost', 'Well\nShawn', 'well \ncontrol', 'well at', 'Well\nAbu', 'Well\nSajeev', 'Well name'] | The Daily Mud Report for well ZK-411 in the Zakum field, operated by ADNOC Offshore, details operations on 28/01/21, including a suspension due to COVID-19 crew shortages, with the well monitored at 3280 ft and filled with 4 bbl of mud. | 2025-07-15T05:16:42.555284
Hi-ISLD-VII-PPC-DMR-65_02-April-2021.pdf | Other Group | pdf | ['28/01/21', '4/2/2021'] | ['Well ID', 'Well name', 'Well Cost'] | The document "Hi-ISLD-VII-PPC-DMR-65_02-April-2021.pdf" details operations for well ZK-411 in the Zakum field, UAE, on 28/01/21, including running a 6 5/8" liner from 8057 ft to 10645 ft and encountering an obstruction at 17405 ft, with significant data on mud properties and drilling parameters. | 2025-07-15T05:16:44.974125
Hi-ISLD-VII-PPC-DMR-13_09-Feb-2021.pdf | Other Group | pdf | ['2/9/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well Cost'] | The document "Hi-ISLD-VII-PPC-DMR-13_09-Feb-2021.pdf" details the drilling operations for well ZK-411 in the Zakum field, Abu Dhabi, conducted by ADNOC Offshore on January 28, 2021, with key activities including drilling a 16" hole section from 1961 ft to 3473 ft using rotary and slide mode, and managing dynamic losses with HVP sweeps. | 2025-07-15T05:16:46.423948
Hi-ISLD-VII-PPC-DMR-44_12-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/12/2021'] | ['Well ID', 'Well Cost', 'Well\nShawn', 'well at', 'Well\nAbu', 'Well\nSajeev', 'Well name'] | The daily mud report for well ZK-411 in the Zakum field, operated by ADNOC Offshore, details operations on January 28, 2021, including monitoring the well at 3280 ft due to a crew shortage caused by COVID-19, with no losses reported. The report includes specific data on mud properties, bit hydraulics, and solids control equipment, with a total well cost of $1,435,360.68 and cumulative product costs of $778,906.66. | 2025-07-15T05:16:48.004554
Hi-ISLD-VII-PPC-DMR-62_30-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/30/2021'] | ['Well ID', 'Well Cost', 'well on', 'well and', 'Well name'] | The document is a Daily Mud Report for the well ZK-411 in the Zakum field, operated by ADNOC Offshore, dated January 28, 2021, detailing various drilling parameters and operations, including circulation activities, bit hydraulics, and solids control equipment. The report includes specific data such as a hole depth of 20,300 ft, dynamic losses of 5 BPH, and the use of 700 gpm & 2050 psi for circulation. | 2025-07-15T05:16:49.732110
Hi-ISLD-VII-PPC-DMR-28_24-Feb-2021.pdf | Other Group | pdf | ['2/24/2021', '28/01/21'] | ['Well ID', 'Well name', 'Wellhead', 'Well Cost'] | On January 28, 2021, ADNOC Offshore conducted operations on well ZK-411 located in the Zakum field, Abu Dhabi, with key activities including the continuation of a 9 5/8" casing cement job using 169 barrels of 16.1 PPG Duraset tail slurry and subsequent displacement with various fluids, and the receipt of 995 barrels of base oil from A-227. | 2025-07-15T05:16:51.255517
Hi-ISLD-VII-PPC-DMR-72_09-April-2021.pdf | Other Group | pdf | ['28/01/21', '4/9/2021', '9/4/2021'] | ['Well ID', 'Well name', 'Well Cost'] | On April 9, 2021, operations at well ZK-411 in the Zakum field, Abu Dhabi, included running upper completion and various assembly installations, with significant activities such as backloading 1200 bbl RDF NAF to A-221 and cleaning tanks, while the centrifuge and filtration operators left the location. | 2025-07-15T05:16:52.315250
DMR1.pdf | Other Group | pdf | ['1/29/2021', '29/01/21'] | ['Well ID', 'Well name', 'Well Cost'] | On January 29, 2021, ADNOC Offshore conducted drilling operations at well ZK-88 located in the Zakum field, Abu Dhabi, UAE, with the rig HI-ISLAND VII. The daily mud report, managed by engineers Mohamed Tawfik and Arshad Mehmood, indicated a total well cost of $1075.00 with no additional costs or mud losses reported. | 2025-07-15T05:16:54.766554
Hi-ISLD-VII-PPC-DMR-32_28-Feb-2021.pdf | Other Group | pdf | ['2/28/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well Cost'] | On January 28, 2021, ADNOC Offshore's rig HI-ISLAND VII, operated by SHELF Drilling, drilled an 8 1/2" hole at the ZAKUM field from 10700 ft to 12350 ft, with significant operations including a wiper trip from 11225 ft to 9444 ft and circulation with 510 GPM at 2750 psi. Key personnel included engineers Mohamed Tawfik and Arshad Mehmood, and the report detailed mud properties, bit hydraulics, and solids control measures. | 2025-07-15T05:16:56.462526
Hi-ISLD-VII-PPC-DMR-2_29-1-2021.pdf | Other Group | pdf | ['1/29/2021', '28/01/21'] | ['Well ID', 'Well name', 'Well Cost'] | On January 28, 2021, ADNOC Offshore conducted operations on the rig HI-ISLAND VII, including moving the rig to well ZK-307, performing maintenance on the draw works, and positioning the rig with final placement at 09:30 hrs; Petrochem mud engineers boarded on January 29, 2021, to update inventory and check equipment. | 2025-07-15T05:16:57.666686
Hi-ISLD-VII-PPC-DMR-45_13-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/13/2021'] | ['Well ID', 'Well Cost', 'Well\nShawn', 'well at', 'Well\nAbu', 'Well\nSajeev', 'Well name'] | On March 13, 2021, operations on well ZK-411 in the Zakum field, Abu Dhabi, were suspended due to a crew shortage caused by COVID-19, with the well being monitored at 3280 ft and no losses reported. The report includes detailed mud properties, circulation data, and solids control equipment status, with a cumulative product cost of $778,906.66 and a total well cost of $1,438,244.94. | 2025-07-15T05:16:59.378022
Hi-ISLD-VII-PPC-DMR-47_15-Mar-2021.pdf | Other Group | pdf | ['28/01/21', '3/15/2021'] | ['Well ID', 'Well Cost', 'well \ncontrol', 'well at', 'Well\nAbu', 'Well\nSajeev', 'Well name'] | The Daily Mud Report for well ZK-411 in the Zakum field, operated by ADNOC Offshore, details operations on January 28, 2021, including a suspension of activities due to a crew shortage caused by COVID-19, with monitoring at 3280 ft and specific mud treatments and well control measures in place. | 2025-07-15T05:17:00.357839
UZ033 Procedure 1 SP.pdf | Other Group | pdf | [] | ['Well \nUZ033', 'Well \n \n1', 'Well specific'] | The document outlines the procedure for Plug and Abandonment (P&A) operations on Well UZ033 at Platform PW054, with key personnel including Completion & Workover Engineer Zakaria Awda and approvals by Engineering Manager Melanie Mikula and Operations Manager George Jarvis, dated June 3, 2022. | 2025-07-15T05:17:01.211912
Hazard Analysis and Risk Control (Risk Assessment).pdf | Risk Assessment and Hazard Analysis | pdf | ['08/30/2020', '10/07/2022', '60/40-70'] | ['Well \nControl', 'well Well', 'Well kill', 'Well-bore', 'Well Killing', 'Well control', 'wellbore', 'Well \ncontrol', 'well \nLoss', 'Wellbore', 'Well Control'] | The Hazard Analysis and Risk Control Report (RA-2020-000007) for PPC Drilling Fluids/Offshore, assessed on 08/30/2020, details various risks and control measures for drilling operations, including the use of BENTONITE polymer mud in 16" holes and 12 1/4" NAF wells, with key risks such as stuck pipe, well control events, and loss of tools/BHA, and specifies preventive measures like maintaining sufficient barite stocks and preparing for cement plugs. The assessment team included Mohamed Farouk and Patrik Cekada, with the last modification made by Fath Elfahal on 10/07/2022. | 2025-07-15T05:17:02.787105
PPC Mud Program UZ- 033 Rig Diyina_Cut Casing and Surface Plug_V1_6 Jun 2022-signed.pdf | Mud Program | pdf | ['28-10-2020', '4/10/2014', '6/23/2016'] | ['WELL SCHEMATIC', 'wellhead', 'Well Cost', 'well is', 'well and', 'Well Killing', 'well bore', 'well with', 'Well Control', 'Well Schematics', 'well for', 'Well Schematic', 'well displace', 'well in', 'Well Chemicals', 'WELL KILLING', 'WELL SCHEMATICS', 'Well Suspension', 'wells', 'wellbores', 'Well UZ-033', 'well within', 'wellbore', 'well control', 'WELL SYNOPSIS', 'WELL CHEMICALS', 'well \n0', 'well back', 'well deviation', 'well the', 'well \nclean'] | The document "PPC Mud Program UZ-033 Rig Diyina_Cut Casing and Surface Plug_V1_6 Jun 2022-signed.pdf" outlines the drilling fluids program for well UZ-033 (PC 13) on Rig Diyina, focusing on the procedures for cutting casing and placing a surface plug, with key dates including preparation on 6 June 2022 and approval on 9 June 2022. The document includes detailed operational steps, well schematics, and safety considerations, with contributions from PPC Project Engineer Andrey/Saumit and approvals from ADNOC Offshore Drilling Fluids Team. | 2025-07-15T05:17:04.668870
Diyina - UZ-033- Chemical Consumption.pdf | Chemical Consumption | pdf | [] | [] | The document details the chemical consumption for well UZ-033, operated by ADNOC Offshore using the Diyina rig, with operations starting on 01.07.2022 and completing on 26.07.2022. Key chemicals used include TRUZAN DS, TRUSCAV HS, and NO-OX EB, with specific quantities and unit prices listed for each. | 2025-07-15T05:17:09.297175
Diyina - UZ-033- Engineering Ticket 1.pdf | Engineering Tickets | pdf | ['25-06-2022', '30-06-2022', '30/06/2022'] | ['well site', 'WELL NO'] | The document "Diyina - UZ-033- Engineering Ticket 1.pdf" details the mud engineering services provided by Petrochem Performance Chemicals Limited L.L.C. for ADNOC Offshore on well UZ-033 at the Diyina rig from June 25, 2022, to June 30, 2022, with Sami Ullah Khan as the lead engineer. The service quality assessment, completed on June 30, 2022, indicates that the performance consistently exceeded expectations across various criteria. | 2025-07-15T05:17:20.750263
Diyina - UZ-033- Engineering Ticket 2.pdf | Engineering Tickets | pdf | ['01-07-2021', '01/07/2022', '05-07-2021', '05/07/2022', '19-07-2021', '23/07/2022', '26-07-2021', '26/07/2022'] | ['well site', 'WELL NO', 'well maintained'] | The document "Diyina - UZ-033- Engineering Ticket 2.pdf" details the engineering services provided by Petrochem Performance Chemicals Limited L.L.C. for ADNOC Offshore on Rig DYINA, Well No. LT-033, with operations conducted from 01-07-2021 to 05-07-2021 and 19-07-2021 to 26-07-2021, totaling 5 and 8 days respectively. The service quality assessment for Lead Drilling Fluids Engineer Samil Shirin Islan, covering job dates 01/07/2022 - 05/07/2022 and 23/07/2022 - 26/07/2022 at ZADCO (Zakum), was signed by Drilling Supervisor Zhander Zhanilov on 26-Jul-22. | 2025-07-15T05:17:32.661265
DF Contractor Feedback Form UZ-033-signed.pdf | Contractor Feedback | pdf | ['07/01/2022', '07/05/2022', '18-7-2022', '26-7-2022', '28-7-2022', '28/7/2022'] | ['Well UZ', 'Well UZ-033', 'Well Name', 'Well \nUZ-009', 'Well Date'] | Operations on Well UZ-033 commenced on 01/07/2022 and concluded on 05/07/2022, with a subsequent switch to Well UZ-009 from 05/07/2022 to 18/07/2022, and resumption of operations on UZ-033 from 18/07/2022 to 26/07/2022. The planned chemical cost was $97,544.01, while the actual cost was $16,992.55, resulting in a significant cost variance due to the inclusion of a contingency product and shorter-than-expected drilling time. | 2025-07-15T05:17:34.285883
Diyina - UZ-033- Well Recap.pdf | Well Recap | pdf | ['01/07/2022', '26/07/2022'] | ['Well ID', 'Well UZ009', 'Well Summary', 'well test', 'Well Name', 'Well Section', 'Well \nUZ'] | The final recap for Well UZ-033, operated by ADNOC OFFSHORE and drilled by ADNOC - DRILLING, details operations from July 1 to July 26, 2022, including drilling 177 feet of cement with a 9.3 ppg CaCl2 brine, at a cost of $16,992.55 for 1398.59 barrels of fluid. Key operations included drilling out a cement plug, running a junk mill, and cutting casing, with significant attention to fluid management and equipment performance. | 2025-07-15T05:17:37.954874